January

February

3/15 - board to approve of timeline

Please approve of sponsor letter as I am not an “official” spokesperson of the board

Set up Raffle ticket system

Get photos of the cabin as soon as possible. Anyway we can scrape off the internet?

Build poster for Cabin Raffle / Save the date poster for camp along with go live ticket sales

- Cabin details - may create separate poster for cabin

- Dates

  - Cabin Raffle

  - Event dates

  - Member ticket sales

  - Non- member ticket sales

- Age

- Cost member, non member

- Tent member, non member

Nightcat to send out sponsor letter after review

March

3/11 mosh -SELL RAFFLE TICKETS online and at mosh push push push board and ambassador welcome committee should be talking about this

April - Anniversary month

4/8 Anniversary mosh

Raffle sales end pull winner end of mosh

4/9 Membership tickets and tent reservation go live Sunday after mosh

Nightcat to follow up again with sponsors who did not respond

- Nightcat will take a peak at claw vendor list and see if there are more possible sponsors to reach out to.

May

5/13 Members only ticket and tent sale end last chance to buy before open to non member

5/14 non member ticket and tent sales go live

June - Pride

June 1st deadline closes for sponsorship

Get all sponsor logo onto some kind of poster arrangement to place on website as a thank you

Must have list of raffle items and value

July

July 1- all raffle items must be in mail (SEAPAH mailbox or my own)

Some kind of posting to thank sponsors and start teasing out the raffle

Middle of july Nightcat to collect all raffle items

August - Action time!

Nightcat - Raffle

- Photograph all raffle item

- Make master raffle list for Emcee

- Make master raffle list per state law so we stay on their good side

- Make boxes

- Make sure we have enough raffle tickets

Early august tease out raffle more

Cancel August mosh?

September

Follow up meeting

What went well

What needed improvement

Nightcat to send thank you letter to all of our sponsors