9/14/2023 Events & Fundraising Meeting

Chair: Domino

Notes: Sinn

Attending:  Eddie, Squirt, Tye, Boned

18+ Women, non-binary and trans Mosh (Squirt) –

- Proposed dates: Oct 21 or Nov 18 (2-4pm)

- Target audience for advertising & promotion is women, non-binary and trans. Can’t exclude anyone but if anyone asks we can let them know they are welcome.

- Venue:

  - Subspace ($900 weekend nights, $750 daytime – might be cost prohibitive for this time)

  - Wild Rose: Domino will reach out to.

  - Need someone to bring mats

  - Still have left over water

  - Squirt can bring snacks

- Need promotional materials.

- Depending on response, could make it a quarterly event.

Suicide Awareness Walk (Oct 22)

- On the calendar and ready to go

Movie Night (Oct 24) –

Per Tye: Movie night is set. Going to try and set up tickets for next weekend w/ option to donate.

- Tye will publish event when ticketing situation is figured out.

- Board chat will decide if its Members only or Members and +1 (non-member ok).

- Donations welcome. Can have jar.

Best in Show (Nov 11) –

- Lumberyard confirmed

- Chair: Domino

- We have venue at 5:00pm. Start show @ 6:30pm – wrap up at 8:30pm.

- Exclusively us on stage side.

- Ticketed event or suggested donation?

- Need to start soliciting performers now.

- Sinn reached out to John (Seattle Leather Daddy 2023) to see if SEA Men in Leather would like to partner. John is reaching out to the board and will get back to us. Performance type paired with puppy.

- Need to create flyer. Domino will look into photoshoot from last year.

- Domino knows a couple drag queens that could be hosts.

Unleashed (Feb 17 or 24) –

- Gallery Erato – Feb not available.

- Domino to check into Sub Space (in Tukwila) instead and see if these dates are available. ($900 weekend nights, $750 daytime)

Holiday Party (Dec 9)

- After mosh like last year.

- Need a teaser poster created to hype it.

Seattle Erotic Arts (End of April) –

- Domino: Still on radar to reach out to Sophia @ Gallery Erato about working bar or coat-check.

September Walkies to State Fair (Domino) -

- Not enough time.