Organisation Notes:-

| Note | Action | Done | Date |
| --- | --- | --- | --- |
| -Set up Masters Games bank account | Using club account | Yes | 9/2/16 |
| -Copy of Insurance Policy | Done. Sent to MG co-ordinator | Yes | 9/2/19 |
| -Cleaning during the games | Club to do the courts. Hall only cleaned twice a week so club will need to do daily. Hire big bin for extra rubbish and split cost with table tennis |  |  |
|  | Room outside toilets for Sports Med. |  |  |
|  | Classrooms still being used by school if needed. |  |  |
| -Canteen | Van has offered to run Canteen. Lyn to do expression of interest for table tennis and school to see if anyone else wants to do catering. |  |  |
| -Publicity- who, what, when, how | Send out flyer to Governing bodies | Yes | 9/2/16 |
|  | Update face-book page new logo and master games logo to be added on |  |  |
|  | Interview with Kieran Satour-M.G. Bulletin | Yes | 22/4/16 |
|  | Send flyer to Kay for redistribution | Yes | 9/2/16 |
|  | Send flyer to past players | Yes | 9/2/16 |
| -Email addresses for interstate badminton associations to distribute to members | Letitia has sent out flyers. MG office making sure on events calendar for peak bodies. Lyn sent out to interstate clubs | Yes | 28/03/16 |
| - Create information pack for emailing after entry | Letitia has the list |  |  |
| -Create and accept flyer for distribution | Letitia has designed a draft poster | Yes | 9/2/16 |
| -Check with Kay re rules, code of conduct and dress code | Lyn to contact Kay – waiting on a reply Use B.A. rules |  |  |
| -Check and confirm booking and costs with Chifley | Booking confirmed. $42.00 menu selected. Room hire $190. Need to set ticket price. | Yes |  |
| -List of equipment needed to run the games | Start list and add on as necessary | Ongoing |  |
| -Purchase of shuttles | Test shuttles from S.A | Ongoing |  |
| -Decision of software program | Software purchased. Cal to do computer work. Lyn going to Darwin to see learn to run a tournament | Yes | 22/3/16 |
| -Possible budget using last year’s figures | Lyn to create (ongoing) |  |  |
| -Roles for people involved in organising the games | Continue developing |  |  |

Financial Predictions

Income:

| Event | No of Players | Entry Fee | Total |
| --- | --- | --- | --- |
| Teams | 9 teams of 6 players | 54 x $45 | $2430 |
| Individuals | 63 | 63 x $65 | $4095 |
|  |  |  | TOTAL $6525 |

Costs

| Item | Provider | Quantity | Cost | Notes |
| --- | --- | --- | --- | --- |
| Hall Hire | OLSH | 7 days | $1000 | Email from Ian |
| Shuttles | Calibre | 50 dozen | $1500.00 |  |
| Airfare from Melb | Qantas | Return fares | $351 + $289 | Booked |
| Reimbursement | Kay Coady | 7 days | $250 | Lost wages |
| Stationary | Paper, Printer Ink, blue tack, pens, textas, whiteout, pencils, rubbers, paperclips, etc |  |  |  |
| Equipment | Microphone, speakers, music, podium, table for medals, seats for VIP guests and ambassadors, printer, folders, laptop, tournament software, internet, brooms, mop and bucket, towels, |  |  |  |
| Sports Med | Esky, ice, cold packs or plastic bags, first aid kit, table with mat, towels, |  |  |  |

Roles for Masters Games

| Role | Person | Responsibilites |
| --- | --- | --- |
| Sports Coordinator | Lyn Ansell | -Liase with MG office -Complete all paperwork on time -Ensure all jobs are allocated and done -Deal with all enquiries and emails -Collect and collate entries -Ensure all equipment is ordered and delivered on time |
| Sports President | Jacob Koshy | -Promote badminton -Oversee running of the games -Deal with disputes/problems |
| Results Coordinator | Cal McMahon / Warren Scale | -Create an excel spreadsheet for results to be recorded -Email results to MG office every day at the end of play -Liaise with Tournament Programmer to ensure results are entered correctly at the end of each match |
| Sports Medicine Officers | Dow Williams | -Complete sports med course and other requirements -Provide at least one sports medicine person at the courts whilst badminton is being played |
| Court Coordinator | Lyn Ansell | -Ensure nets are erected correctly and at the proper height -Sweep between matches and mop at night -Pick up used shuttles and dispose of each day -Provide chairs for line judges in the correct positions |
| Tournament Programmer | Cal McMahon | -Enter all data into the tournament software -Ensure the draw is displayed as early as possible the day before competition -Enter all results into the computer and update the scores at the end of each day -Liase with Results Coordinator to get results to MG office at the end of play each day |
| Presentation Night Coordinator | Lyn Ansell | -Create and sell tickets for the presentation night -Ensure money and tickets balance -Liaise with Chifleys regarding numbers and room requirements -Decorate room |